## Sheet1
Tasks | Start Date | End Date | Time taken
Design and create a HUD | 2025-02-24 | 2025-02-26 | 2
Implement player movement logic | 2025-02-24 | 2025-02-27 | 3
Code the start menu buttons | 2025-02-24 | 2025-02-28 | 4
Design the UI for buying property | 2025-02-26 | 2025-03-01 | 3
Code the logic behind the jail board tile | 2025-02-27 | 2025-03-01 | 2
Import player tokens models into Unity | 2025-02-28 | 2025-03-08 | 8
Code the logic behind the parking board tile | 2025-03-01 | 2025-03-03 | 2
Design the UI for "pot luck" cards | 2025-03-01 | 2025-03-05 | 4
Code the "pot luck" cards | 2025-03-02 | 2025-03-06 | 4
Create a token selection screen | 2025-03-03 | 2025-03-13 | 10
Design the UI for "opportunity knocks" cards | 2025-03-05 | 2025-03-09 | 4
Code the "opportunity knocks" cards | 2025-03-06 | 2025-03-10 | 4
Documentation | 2025-03-07 | 2025-03-13 | 6
Code the card selection and shuffling mechanism | 2025-03-08 | 2025-03-10 | 2
Implement interface switching | 2025-03-09 | 2025-03-13 | 4
Implement camera transition | 2025-03-09 | 2025-03-13 | 4
Testing | 2025-03-10 | 2025-03-13 | 3