## Sheet1
Tasks | Start Date | End Date | Time taken
Add a skybox to the game's background | 2025-03-14 | 2025-03-16 | 2
Implement interface switching | 2025-03-14 | 2025-03-17 | 3
Import and configure player tokens in Unity | 2025-03-14 | 2025-03-17 | 3
Create a token selection screen | 2025-03-14 | 2025-03-19 | 5
Create and import models for houses and hotels | 2025-03-16 | 2025-03-22 | 6
Implement camera transition | 2025-03-17 | 2025-03-20 | 3
Code the logic behind the banking system | 2025-03-19 | 2025-03-21 | 2
Code the logic behind buying properties | 2025-03-21 | 2025-03-24 | 3
Documentation | 2025-03-23 | 2025-03-31 | 8
Code the logic behind paying rent | 2025-03-24 | 2025-03-27 | 3
Integrating volume controls to affect in-game audio | 2025-03-25 | 2025-03-28 | 3
Code the logic behind selling properties | 2025-03-27 | 2025-03-31 | 4
Testing | 2025-03-28 | 2025-03-31 | 3