## Sheet1
Tasks | Start Date | End Date | Time taken
Creating an animation for the start screen | 2025-04-01 | 2025-04-02 | 1
Implement and configure models for houses and hotels | 2025-04-01 | 2025-04-02 | 1
Create a game-mode selection screen | 2025-04-01 | 2025-04-03 | 2
Code the logic for auctioning a property | 2025-04-02 | 2025-04-04 | 2
Create the window to display the bidding system | 2025-04-02 | 2025-04-05 | 3
Improvements to the UI for property cards | 2025-04-02 | 2025-04-05 | 3
Code the logic for improving the property | 2025-04-04 | 2025-04-06 | 2
Documentation | 2025-04-04 | 2025-04-11 | 7
Improvements to the UI of non-standard property cards | 2025-04-05 | 2025-04-07 | 2
Create and implement a property review window | 2025-04-05 | 2025-04-08 | 3
Code the logic for selling the houses and hotels | 2025-04-06 | 2025-04-08 | 2
Testing & Bug Fixing | 2025-04-07 | 2025-04-11 | 4